## Features
Project: hailua.com.vn | Selling clothes system
Team: 5 | Group8
ID | Feature Name | Description | Remark
UC01 | Login as admin | Use admin account to login to admin's site
UC02 | Import items (admin role) | Admin use this feature to import items feature
UC03 | Manage items (admin role) | Admin use this feature to view, edit, delete, search item
UC04 | Add items to cart (customer role) | Customer use this feature to add item they want to buy into cart
UC05 | Manage items in cart (customer role) | Customer use this feature to manage items they added into cart

## Test cases
Function/Feature ID | Case ID | Test case name | Test step | Expected Result (ER) | Actual Result | Status | Tester | Tested Date | Remark
Function 01: Login as admin
UC01 | UI01 | Log in with correct username and password | 1. Enter User Name: "abcd " 2.Enter Password: "abcd" 3. Click "Ok" button | Connect successfully to admin site | Working smoothly as expected | Pass | Đăng Triều | 2021-05-13
UC01 | UI02 | Log in with incorrect username | 1. Enter User Name: "abcx" 2. Enter Password: "abcd" 3. Click "Ok" button | 1. Unauthenticated 2. A wrong user-account notice will be displayed | 1. Unauthenticated 2. No notice is shown | Pass | Đăng Triều | 2021-05-13
UC01 | UI02 | Log in with incorrect username | 1. Enter User Name: "abcx" 2. Enter Password: "abcd" 3. Click "Ok" button | 1. Unauthenticated 2. A wrong user-account notice will be displayed | 1. Unauthenticated 2. No notice is shown | Pass | Đăng Triều | 2021-05-13
UC01 | UI03 | Login with blank User name/Password | 1. Enter User Name: " " 2. Enter Password: " " 3. Click "Ok" button | 1. Disallows the user to proceed and 2. The error message should be displayed | 1. Disallows the user to proceed and 2. The error message "Please fill out this field" display | Pass | Đăng Triều | 2021-05-13
UC01 | UI04 | Login with Special characters of User name and Password. Use to prevent SQL injection | 1. Enter User Name: " 'or'$'='$' " 2. Enter Password: " 'or'$'='$' " . Click "Ok" button | 1. Disallows the user to proceed 2. Show special key word not allow | working as wrong username/password | Fail | Đăng Triều | 2021-05-13
Function 02: Import items (admin role)
UC02 | UI06 | Import item normally | 1. Enter product Name: "Jacket 1" 2.Choose product category: "Jacket" 3.Choose product brand: "Hermes" 4.Choose product image: "abc.jpg" 5.Choose product type: "Feathered" 6.Choose product gender: "Male" 7.Choose product price: "15000" | Display "Insert Product Successfully" message | Display "Insert Product Successfully" message | Pass | Đức Hoàng | 2021-05-13
UC02 | UI07 | Import exist item | 1. Enter product Name: "Jacket 1" 2.Choose product category: "Jacket" 3.Choose product brand: "Hermes" 4.Choose product image: "abc.jpg" 5.Choose product type: "Feathered" 6.Choose product gender: "Male" 7.Choose product price: "15000" | 1. Disallows the user to proceed and 2. The error message should be displayed | Display "Insert Product Successfully" message | Fail | Đức Hoàng | 2021-05-13
UC02 | UI08 | Import item with blank name field | 1. Enter product Name: "" 2.Choose product category: "Jacket" 3.Choose product brand: "Hermes" 4.Choose product image: "abc.jpg" 5.Choose product type: "Feathered" 6.Choose product gender: "Male" 7.Choose product price: "15000" | 1. Disallows the user to proceed and 2. The error message should be displayed | 1. Disallows the user to proceed and 2. The error message "Fields must be not empty" displayed | Pass | Đức Hoàng | 2021-05-13
UC02 | UI09 | Import item with blank image field | 1. Enter product Name: "Jacket 1" 2.Choose product category: "Jacket" 3.Choose product brand: "Hermes" 4.Choose product image: "" 5.Choose product type: "Feathered" 6.Choose product gender: "Male" 7.Choose product price: "15000" | 1. Disallows the user to proceed and 2. The error message should be displayed | 1. Disallows the user to proceed and 2. The error message "Fields must be not empty" displayed | Pass | Đức Hoàng | 2021-05-13
UC02 | UI10 | Import item with blank brand field | 1. Enter product Name: "Jacket 1" 2.Choose product category: "Jacket" 3.Choose product brand: "" 4.Choose product image: "abc.jpg" 5.Choose product type: "Feathered" 6.Choose product gender: "Male" 7.Choose product price: "15000" | 1. Disallows the user to proceed and 2. The error message should be displayed | Display "Insert Product Successfully" message but not add new product into list | Fail | Đức Hoàng | 2021-05-13
UC02 | UI11 | Import item with blank category field | 1. Enter product Name: "Jacket 1" 2.Choose product category: "" 3.Choose product brand: "Hermes" 4.Choose product image: "abc.jpg" 5.Choose product type: "Feathered" 6.Choose product gender: "Male" 7.Choose product price: "15000" | 1. Disallows the user to proceed and 2. The error message should be displayed | Display "Insert Product Successfully" message but not add new product into list | Fail | Đức Hoàng | 2021-05-13
Function 03: Manage items (admin role)
UC03 | UI12 | Edit item's name field | 1. Update product Name: "Jacket 2" | Display successfully message and save new item's update info | Display "Product Updated Successfully" message | Pass | Bá Tín | 2021-05-13
UC03 | UI13 | Edit item's category field | 1. Update category: "Short" | Display successfully message and save new item's update info | Display "Product Updated Successfully" message | Pass | Bá Tín | 2021-05-13
UC03 | UI14 | Edit item's brand field | 1. Update brand: "Channel" | Display successfully message and save new item's update info | Display "Product Updated Successfully" message | Pass | Bá Tín | 2021-05-13
UC03 | UI15 | Edit item's image field | 1. Update category: "download.jpg" | Display successfully message and save new item's update info | Display "Product Updated Successfully" message | Pass | Bá Tín | 2021-05-13
UC03 | UI16 | Edit item's price field | 1. Update price: "20000" | Display successfully message and save new item's update info | Display "Product Updated Successfully" message | Pass | Bá Tín | 2021-05-13
UC03 | UI17 | Search item | Enter item name | Display item with appropriate name | Display item with appropriate name | Pass | Bá Tín | 2021-05-13
Function 04: Add items to cart (customer role)
UC04 | UI18 | Add 1 item to cart | 1. Choose item want to add 2. Choose quantity: 1 3. Click confirm | Display successfully message and add item to cart with 1 quantity | Display "Thêm sản phẩm thành công" message And add item into cart | Pass | Hồng Quang | 2021-05-13
UC04 | UI19 | Add 0 item to cart | 1. Choose item want to add 2. Choose quantity: 0 3. Click confirm | Display error message | Display error message "Quantity must be greater than or equal to 1" message | Pass | Hồng Quang | 2021-05-13
UC04 | UI20 | Add 1 million item to cart | 1. Choose item want to add 2. Choose quantity: 1000000 3. Click confirm | Display error message not enough quantity | Display "Thêm sản phẩm thành công" message And add item into cart | Fail | Hồng Quang | 2021-05-13
Function 05: Manage items in cart (customer role)
UC05 | UI21 | Update item'quantity in cart | 1. Choose item want to update quantity 2. Choose new quantity: 2 3. Click update | Display successfully message, update item quantity and price | Update new quantity and price | Pass | Thùy Dương | 2021-05-13
UC05 | UI22 | Delete item in cart | 1. Choose item want to delete 2. Click delete | Delete item | Display confirm message and if customer click confirm then delete the item | Pass | Thùy Dương | 2021-05-13